## Slide 1: Rackspace Development Center
Program Name | Global Data – Core Datasets
Reported Duration | Mar 23rd to Mar 29th
Program Start Date | Mar 17th, 2015
Program Sponsor | Nick Kolegraff
Rackspace Manager | Greg Nelson
Overall Status | GREEN

## Slide 2: Program status
Project | Budget | Schedule | Quality | Issues | Comments
Tools Migration |  |  |  |  | Team running 1 week behind schedule
Billing Events |  |  |  |  | Quality issues and performance issues.
Marketing |  |  |  |  | No issues
Tickets Re-architecture |  |  |  |  | No issues
Additional Comments:
1) SoW yet to be approved

## Slide 3: Major accomplishments
Billing Events:
  All artefacts for dimensions have been delivered for QE. No issues reported as yet
Marketing:
  ACG to ODBC replacement successfully completed. Ready to move to QE.
Tools Migration:
  Incident Dimensions TADS implementation completed and ready for QE.
Tickets Re-architecture:
  Analyzed all existing dimensions and facts against the conceptual models
  8 New questions identified
Other accomplishments:
  Entire team has been educated on TADS implementation
  Additional code review steps added based on lessons learnt in Billing Events project.

## Slide 4: Previously planned but incomplete activities
Activity | Owner | Planned End Date | Projected End Date | Reason for Delay
Fact Billing Events | Vamsi | 3/26/2015 | 3/31/2015 | Dependencies on test data from production to be copied

## Slide 5: Planned activities for upcoming period
Billing Events:
  To Work with QE to move the code to production by the end of the week.
Marketing:
  TADS implementation in Site Visits
Tools Migration:
  Continue TADS implementation
Tickets Re-architecture:
  Analyze all the source systems, existing QlikView reports/dashboards and come up with more questions
Other planned tasks:
  Fact Recycling PoC
  Error dimension
  Work with Rajani on Dependency model
  Work with Sruthi/Greg on standardizing naming conventions

## Slide 6: Effort summary
Person | Role | Current Week | Sum To Date
Naga Parna | Lead Engineer | 40 | 72
Aswani Yadavilli | Architect | 40 | 72
Sravan Konde | Lead Engineer | 40 | 72
Vamsi Bala | Data Engineer | 40 | 72
Uday Kumar Vommi | Data Engineer | 40 | 72
Kranthi Kumar Soma | Data Engineer | 40 | 72
Somenath Chakraborty | Data Engineer | 8 | 8
Shaheeb Rahman | Data Engineer | 40 | 72
Total |  | 288 | 512