## Slide 1: Rackspace Development Center
Program Name | Global Data – Core Datasets
Reported Duration | Apr 13th to Apr 17th
Program Start Date | Mar 17th, 2015
Program Sponsor | Nick Kolegraff
Rackspace Manager | Greg Nelson
RDC Owner | Aswani Yadavilli
Overall Status | GREEN
Prior Week Status | GREEN

## Slide 2: Program status
Project | Budget | Schedule | Quality | Issues | Comments
Tools Migration |  |  |  |  | None
Billing Events |  |  |  |  | None
Marketing |  |  |  |  | None
Tickets |  |  |  |  | None
Other Projects |  |  |  |  | 
Additional Comments:
SoW yet to be approved

## Slide 3: Major accomplishments
Usage (Billing Events):
  Post Go-live issues identified and resolved in dimensions – Team and Instance have been resolved.
  Further analysis is being done on other related issues.
Marketing Acquisition Funnel Enhancements:
  TADS implementation is complete for Site Visits Subject Area
  Staging database reconciliation and PGSQL to SQL Server migration started
Tickets:
  Tickets Created – Logical/Physical Data Modeling done.
  Source Data Analysis for Tickets Created – Core and Encore – Begun
Tools Migration:
  Incidents TADS implementation dev completed.
  All Open Issues in Incident have identified and set aside for analysis along with Tickets design.
Other Accomplishments:
  Fact Recycling PoC – 100% complete.
  Demo scheduled for 4/27

## Slide 4: Previously planned but incomplete activities
Activity | Owner | Planned End Date | Projected End Date | Reason for Delay
Demo for Fact Recycling PoC | Vamsi | 4/24 | 4/27 | Due to non-availability of onsite team due on 4/24

## Slide 5: Planned activities for upcoming period
Marketing:
  TADS implementation in Site Visits
  Team to work on replacing staging from PostgreSQL to SQL Server
Billing Events:
  Team to work on replacing staging from PostgreSQL to SQL Server
Tools Migration:
  Finish TADS implementation
Tickets Re-architecture:
  Finish the Tickets Created PDM. Team to work on SDA for Core & Encore.
Other planned tasks:
  Finish Poc for Fact Recycling. Demo for Thu – 4/23

## Slide 6: Thank you For any questions, Please contact: Aswani Yadavilli aswani.yadavilli@rackspace.com (+1) 210 712 2187