## Slide 1: Rackspace Development Center
Program Name | Global Data – Core Datasets
Reported Duration | Apr 20th to Apr 24th
Program Start Date | Mar 17th, 2015
Program Owner | Nick Kolegraff
Delivery Manager | Greg Nelson
RDC Owner | Aswani Yadavilli
Overall Status | GREEN
Prior Week Status | GREEN

## Slide 2: Program status
Project | Budget | Schedule | Quality | Issues | Comments
Customer Experience – Marketing |  |  |  |  | None
Usage - Billing Events |  |  |  |  | None
Tickets |  |  |  |  | None
Other Projects |  |  |  |  | None
Additional Comments:
SoW yet to be approved

## Slide 3: Major accomplishments
Marketing Acquisition Funnel Enhancements (Uday, Kranthi, Shaheeb):
  TADS implementation is complete for Site Visits Subject Area
  Staging database reconciliation and PGSQL to SQL Server migration started
Tickets (Karteek, Prakash, Sravan, Prasanth):
  Tickets Created PDM Finished.
  Tickets Assigned Conceptual Model Finished.
  Source Data Analysis for Tickets Created – Core and Encore – Begun
Other Projects ( Karteek, Vamsi, Prakash):
  Fact Recycling POC Demo done.
Usage (Billing Events):
  No Major accomplishments this week.

## Slide 4: Previously planned but incomplete activities
Activity | Owner | Planned End Date | Projected End Date | Reason for Delay
Demo for Fact Recycling POC | Vamsi | 4/24 | 4/27 | Due to non-availability of onsite team due on 4/24

## Slide 5: Planned activities for upcoming period
Marketing: (Kranthi & Shaheeb)
  TADS implementation in Site Visits
  Team to work on replacing staging from PostgreSQL to SQL Server
Billing Events (Uday):
  Team to work on replacing staging from PostgreSQL to SQL Server
Tickets (Karteek, Prakash, Sravan, Prasanth):
  Work on Conceptual Model for Tickets Worked and Ticket State. (Karteek)
  Work on Logical, Physical Models for Tickets Assigned. (Karteek, Prakash)
  Team to work on SDA for Core & Encore. (Sravan, Prasanth)
Other Projects (Vamsi, Karteek, Prakash):
  Work with Pete on Integration of Recycling with Dependency Model. (Karteek, Vamsi)
  Demo of Fact Recycling for entire Rackspace Dev Team (Vamsi, Karteek, Prakash)

## Slide 6: Thank you For any questions, Please contact: Aswani Yadavilli aswani.yadavilli@rackspace.com (+1) 210 712 2187