## Slide 1: Rackspace Development Center
Program Name | Global Data – Core Datasets
Reported Duration | Mar 30th to Apr 3rd
Program Start Date | Mar 17th, 2015
Program Sponsor | Nick Kolegraff
Rackspace Manager | Greg Nelson
RDC Owner | Aswani Yadavilli
Overall Status | GREEN
Prior Week Status | GREEN

## Slide 2: Program status
Project | Budget | Schedule | Quality | Issues | Comments
Tools Migration |  |  |  |  | Three days behind schedule
Billing Events |  |  |  |  | ONE week behind schedule
Marketing |  |  |  |  | None
Tickets Re-architecture |  |  |  |  | None
Additional Comments:
SoW yet to be approved

## Slide 3: Major accomplishments
Billing Events:
  QE identified some issues in the deliverables. Issues fixes are being delivered.
Marketing:
  TADS implementation is in progress,
Tools Migration:
  Incident Dimensions TADS implementation completed and ready for QE.
Tickets Re-architecture:
  Ticket Analysis finished and delivered.
Other accomplishments:
  Discussion with Rajani on Recycling and Error handling finished

## Slide 4: Previously planned but incomplete activities
Activity | Owner | Planned End Date | Projected End Date | Reason for Delay
Fact Billing Events | Vamsi | 3/26/2015 | 4/7/2015 | Logic changes were suggested during code review which needed rework

## Slide 5: Planned activities for upcoming period
Billing Events:
  To Work with QE to move the code to production by the end of the week.
Marketing:
  TADS implementation in Site Visits
Tools Migration:
  Continue TADS implementation
Tickets Re-architecture:
  Perform High level architecture
Other planned tasks:
  Fact Recycling Proof of Concept
  Error dimension
  Work with Sruthi/Greg on standardizing naming conventions

## Slide 6: Effort summary
Person | Role | Current Week | Sum To Date
Naga Parna | Lead Engineer | 40 | 112
Aswani Yadavilli | Architect | 40 | 112
Sravan Konde | Lead Engineer | 32 | 112
Vamsi Bala | Data Engineer | 16 | 112
Uday Kumar Vommi | Data Engineer | 32 | 112
Kranthi Kumar Soma | Data Engineer | 32 | 112
Somenath Chakraborty | Data Engineer | 8 | 16
Shaheeb Rahman | Data Engineer | 32 | 112
Total |  | 232 | 800

## Slide 7: Thank you For any questions, Please contact: Aswani Yadavilli aswani.yadavilli@rackspace.com (+1) 210 712 2187