## Slide 1: Rackspace Development Center
Program Name | Global Data – Core Datasets
Reported Duration | Apr 4th to Apr 11th
Program Start Date | Mar 17th, 2015
Program Sponsor | Nick Kolegraff
Rackspace Manager | Greg Nelson
RDC Owner | Aswani Yadavilli
Overall Status | GREEN
Prior Week Status | GREEN

## Slide 2: Program status
Project | Budget | Schedule | Quality | Issues | Comments
Tools Migration |  |  |  |  | None
Billing Events |  |  |  |  | Four Days behind
Marketing |  |  |  |  | None
Tickets Re-architecture |  |  |  |  | None
Additional Comments:
SoW yet to be approved

## Slide 3: Major accomplishments
Billing Events:
  QE identified some issues in the deliverables. Issues fixes are being delivered.
Marketing:
  TADS implementation is in progress
Tools Migration:
  Incident Facts TADS implementation completed and ready for QE.
Tickets Re-architecture:
  Ticket Analysis finished and delivered.
  Logical Modeling for Tickets Created in progress

## Slide 4: Previously planned but incomplete activities
Activity | Owner | Planned End Date | Projected End Date | Reason for Delay
Billing Events Go-live | Entire Team | 4/10/2015 | 4/15/2015 | Unprecedented issues in the QE during first ever rollout of TADS implementation

## Slide 5: Planned activities for upcoming period
Billing Events:
  To ensure Go-live by 4/15
Marketing:
  TADS implementation in Site Visits
Tools Migration:
  Continue TADS implementation
Tickets Re-architecture:
  Logical/Physical model for Tickets
Other planned tasks:
  Fact Recycling Proof of Concept
  Error dimension
  Work with Sruthi/Greg on standardizing naming conventions

## Slide 6: Effort summary
Person | Role | Current Week | Sum To Date
Aswani Yadavilli | Architect | 40 | 152
Naga Parna | Onsite Lead | 40 | 152
Sravan Konde | Lead Engineer |  | 144
Vamsi Bala | Data Engineer |  | 128
Uday Kumar Vommi | Data Engineer |  | 144
Kranthi Kumar Soma | Data Engineer |  | 144
Somenath Chakraborty | Data Engineer |  | 24
Shaheeb Rahman | Data Engineer |  | 144
Prasanth Malisetty | Data Engineer |  | 
Total |  |  | 

## Slide 7: Thank you For any questions, Please contact: Aswani Yadavilli aswani.yadavilli@rackspace.com (+1) 210 712 2187