## Slide 1: Rackspace Development Center
Program Name | Global Data – Core Datasets
Reported Duration | April 27th to May 1st
Program Start Date | Mar 17th, 2015
Program Owner | Nick Kolegraff
Delivery Manager | Greg Nelson
RDC Owner | Aswani Yadavilli
Overall Status | GREEN
Prior Week Status | GREEN

## Slide 2: Program status
Project | Budget | Schedule | Quality | Issues | Comments
Customer Experience – Marketing |  |  |  |  | None
Usage - Billing Events |  |  |  |  | None
Tickets |  |  |  |  | None
Other Projects |  |  |  |  | None
Additional Comments:
SoW yet to be approved

## Slide 3: Major accomplishments
Marketing Acquisition Funnel Enhancements (Uday, Kranthi, Shaheeb):
  Staging database repointing to SQL Server – 100% done
  Staging database reconciliation – 50% done
Tickets (Karteek, Prakash, Sravan, Prasanth):
  Modeling (Karteek) – Dim Ticket
  Source Data Analysis
    (Karteek/Sravan): Encore – 90% done
    (Prakash/Prasanth): Core – 70% done
  Field Mapping
    Encore – 50% done
    Core – 50% done
Other Projects ( Karteek, Vamsi, Prakash):
  Recycling Demo for entire Dev team done.
  Analyzing Dependencies
Usage (Billing Events):
  No Major accomplishments this week.

## Slide 4: Previously planned but incomplete activities
Activity | Owner | Planned End Date | Projected End Date | Reason for Delay

## Slide 5: Planned activities for upcoming period
Tickets (Karteek, Prakash, Sravan, Prasanth):
  Architecture (Karteek) - Logical/Physical Modeling for Tickets Assignment
  SDA (All four) - Finish up on SDA for Core and Encore for Dim Ticket Category, Dim Ticket Status, Dim Ticket Priority, Dim Ticket Severity, Dim Ticket Complexity dimensions
  Field Mapping - Finish up on Field Mapping for Dim Ticket for Core and Encore
  Informatica Mapping - Source to Staging for Dim Ticket for Core and Encore
Marketing: (Kranthi & Shaheeb)
  Finish Staging repointing to SQL Server and Staging Area consolidation for Site visits.
Billing Events (Uday):
  Finish replacing staging from PostgreSQL to SQL Server for Dim Instance and Dim Unit of Measure
Other Projects (Vamsi, Karteek, Prakash):
  Finish modeling tables for recycling and move it to Stage Two.
  Present the modified model to Pete and Rajani for signoff.
  Finish documentation for Recycling

## Slide 6: For any questions, Please contact: Aswani Yadavilli aswani.yadavilli@rackspace.com (+1) 210 712 2187